# Soteria Feature List

Onboarding

* ~~I18N Support~~
* ~~Load Existing Wallet~~
  + ~~Plaintext~~
  + ~~Seed Vault~~
  + ~~Mnemonic~~
* ~~Create Wallet~~
* ~~Export Wallet~~
  + ~~Plaintext~~
  + ~~Seed Vault~~
  + ~~Mnemonic~~
    - ~~Print Template & Full~~
* ~~Encrypt Wallet~~
* ~~Unlock wallet~~

Wallet Dashboard - **19 Hours Left**

* ~~Multi-Account Single Entropy~~
* ~~Sends / Receives~~
* ~~Token Sends~~
* ~~Real-time websockets~~
* ~~Balances~~ & ~~Token Balances (Need to determine best UI for this) -~~ **~~3 hours~~**
* Transaction Information Page - **16 hours**

Tokens List - **22 Hours**

* ~~List of Tokens (Tokens I have history on and or am a controller of) -~~ **~~6 Hours~~**
* ~~Create New Token -~~ **~~6 Hours~~**
* ~~Token Page~~
  + ~~Similar to Node Explorer but with the ability to invoke actions -~~ **~~10 hours~~**

Node Integration & Settings - **50 Hours?**

* Download or bundle the binary - **8 Hours?**
* Execute the binary - **8 Hours?**
* Bootstrapping status UI progress inside Onboarding - **16 Hours?**
* Connect UI to Node via RPC calls - **2-4 Hours**
* Settings for CLI & RPC configurable settings - **16 Hours?**
* TX Acceptor Configuration - **????? Hours**
* BLS Key Management - **????? Hours**

Elections / Governance - **62 Hours**

* Current Elected Delegates - **8 Hours**
  + Go back see history
* Delegate Candidates - **8 Hours**
* Representatives List Page - **16 Hours**
  + My Non-bonded representative
  + My current bonded representatives
  + List of top reps and their rates
* Rep Page - **16 Hours**
  + Voting History
  + Weight
  + Delegators list
* Delegate Page - **16 Hours**
  + Election history
  + ???

Staking - **18 Hours** (should staking be inside the wallet dashboard?)

* Current Stake - **2 Hours**
* Rebond stake - **2 Hours**
* Current Bonding period - **2 Hours**
* Liabilities - **4 Hours**
* Current Reward (only on local mode?) & Claim Reward - **8 Hours**

Fee Page

* TBD

Total: **171 Hours**

Estimated Completion Date: **Aug 31st** (192 work hours till the 16th)